## Projects
name | projectNumber | status | client | description | startDate | endDate | estimatedHours | isActive
Website Redesign | PRJ-2024-001 | active | Acme Corp | Complete website overhaul | 2024-01-01 | 2024-06-30 | 2000 | TRUE
Mobile App Phase 2 | PRJ-2024-002 | planning | TechStart | iOS and Android app development | 2024-03-01 | 2024-12-31 | 3500 | TRUE
Internal Tool Update |  | active | Internal | Update existing dashboard tool |  |  |  | TRUE
Quick Fix Project | QF-001 | completed | Legacy Client | Small bug fixes and updates | 2024-01-15 | 2024-02-15 | 40 | FALSE

## Assignments
projectName | projectNumber | personName | personEmail | roleOnProject | startDate | endDate | weeklyHours | totalHours | notes | isActive
Website Redesign | PRJ-2024-001 | John Smith | john.smith@company.com | Tech Lead | 2024-01-01 | 2024-06-30 | {"2024-01-01":20,"2024-01-08":25,"2024-01-15":20} | 800 | Full-time on project | TRUE
Website Redesign | PRJ-2024-001 | Jane Doe | jane.doe@company.com | UI/UX Designer | 2024-01-15 | 2024-05-15 | {"2024-01-15":30,"2024-01-22":32,"2024-01-29":30} | 600 | Design lead | TRUE
Mobile App Phase 2 | PRJ-2024-002 | John Smith | john.smith@company.com | Consultant | 2024-03-01 | 2024-04-01 | {"2024-03-01":10,"2024-03-08":8} | 72 | Part-time advisory role | TRUE
Internal Tool Update |  | Sarah Wilson | sarah.wilson@company.com | Developer | 2024-02-01 |  | {"2024-02-01":40} | 40 | Quick updates needed | TRUE
Quick Fix Project | QF-001 | Mike Johnson | mike.johnson@company.com | Senior Developer | 2024-01-15 | 2024-02-15 | {} | 40 | Bug fixes completed | FALSE

## Deliverables
projectName | projectNumber | description | percentage | date | sortOrder | isCompleted | completedDate | notes
Website Redesign | PRJ-2024-001 | Schematic Design | 30 | 2024-02-15 | 1 | TRUE | 2024-02-10 | Approved by client
Website Redesign | PRJ-2024-001 | Design Development | 60 | 2024-04-01 | 2 | FALSE |  | In progress
Website Redesign | PRJ-2024-001 | Construction Documents | 90 | 2024-05-15 | 3 | FALSE |  | Not started
Mobile App Phase 2 | PRJ-2024-002 | Requirements Document | 15 | 2024-03-15 | 1 | FALSE |  | Initial draft
Mobile App Phase 2 | PRJ-2024-002 | UI Wireframes | 40 | 2024-04-30 | 2 | FALSE |  | Design phase
Internal Tool Update |  | Database Migration | 100 | 2024-02-28 | 1 | TRUE | 2024-02-25 | Completed successfully
Quick Fix Project | QF-001 | Bug Fixes | 100 | 2024-02-15 | 1 | TRUE | 2024-02-12 | All issues resolved

## Template
PROJECTS TEMPLATE
name | projectNumber | status | client | description | startDate | endDate | estimatedHours | isActive
Website Redesign | PRJ-2024-001 | Active | Acme Corp | Complete website overhaul | 2024-01-01 | 2024-06-30 | 2000 | TRUE
ASSIGNMENTS TEMPLATE
projectName | projectNumber | personName | personEmail | roleOnProject | startDate | endDate | weeklyHours | totalHours | notes | isActive
Website Redesign | PRJ-2024-001 | John Smith | john@company.com | Tech Lead | 2024-01-01 | 2024-06-30 | {"2024-08-25":20,"2024-09-01":25} | 800 | Full-time on project | TRUE
DELIVERABLES TEMPLATE
projectName | projectNumber | description | percentage | date | sortOrder | isCompleted | completedDate | notes
Website Redesign | PRJ-2024-001 | Schematic Design | 30 | 2024-02-15 | 1 | TRUE | 2024-02-10 | Approved by client

## Instructions
Projects Import/Export Instructions
MULTI-SHEET STRUCTURE:
• Projects Sheet: Main project information
• Assignments Sheet: People assigned to projects with weekly hours
• Deliverables Sheet: Project milestones and completion tracking
• Template Sheet: Examples for each data type
PROJECTS SHEET FIELDS:
• name - Project name (REQUIRED)
• projectNumber - Unique project identifier
• status - Planning/Active/Active CA/On Hold/Completed/Cancelled
• client - Client name (default: Internal)
• description - Project description
• startDate/endDate - Date format: YYYY-MM-DD
• estimatedHours - Total estimated hours
• isActive - TRUE/FALSE (default: TRUE)
ASSIGNMENTS SHEET FIELDS:
• projectName/projectNumber - Links to project (REQUIRED)
• personName/personEmail - Links to person (REQUIRED)
• roleOnProject - Person's role on this project
• startDate/endDate - Assignment date range
• weeklyHours - JSON format: {'2024-08-25':10,'2024-09-01':8}
• totalHours - Auto-calculated from weekly hours
• notes - Assignment notes
• isActive - TRUE/FALSE
DELIVERABLES SHEET FIELDS:
• projectName/projectNumber - Links to project (REQUIRED)
• description - Deliverable description (e.g., SD, DD, IFC)
• percentage - Completion percentage (0-100)
• date - Target or completion date
• sortOrder - Display order (lower numbers first)
• isCompleted - TRUE/FALSE
• completedDate - When actually completed
• notes - Additional details
IMPORT PROCESS:
1. Projects are imported/updated first
2. People are matched by email then name
3. Assignments link projects to people
4. Deliverables link to projects
5. All relationships are validated
MATCHING LOGIC:
• Projects: Match by projectNumber (preferred) or name
• People: Match by email (preferred) or name
• Cross-validation ensures all references are valid
WEEKLY HOURS JSON FORMAT:
• Use Sunday dates as keys: '2024-08-25'
• Values are hours for that week: 10, 20, etc.
• Example: {'2024-08-25':20,'2024-09-01':25,'2024-09-08':15}
ERROR PREVENTION:
• Use the Template sheet for proper formatting
• Ensure all required relationships exist
• Use dry-run mode to preview changes
• Check for duplicate project numbers